## Sheet1
Question Type | Question | Option1 | Option2 | Option3 | Option4 | Option5 | Correct Answer | Default Marks | Default Time To Solve | Topic ID | Difficulty Level | Hint | Solution
MSA | What is the primary platform for accessing and submitting e-tenders for MCGM works as mentioned in the document? | Physical submission at the Chief Engineer's office | A third-party e-tendering portal | The MCGM's official portal (http://portal.mcgm.gov.in) | Via email to the Chief Engineer's office | Submission through post | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the minimum required consent percentage of occupiers for reconstruction/redevelopment of a cessed building existing prior to 30/9/1969 under MHAD Act, 1976? | Not less than 70% | Not less than 51% | Not less than 60% | Not less than 80% | Not less than 40% | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | As per the SBD, in the three-stage system of e-tendering, what is required to be deposited along with the Bid? | A performance guarantee | Earnest Money Deposit (EMD) | A bank solvency certificate | A tender processing fee | A hard copy of the bid document | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | How is the Bid Security/EMD to be provided by the Bidders while submitting the bids according to the document? | Through a physical bank challan | Through the payment gateways online | Via a demand draft to the Chief Engineer | By submitting a bank guarantee in Packet A | Directly at the CFC centers in MCGM Ward Offices | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if a bid is not accompanied by the Earnest Money Deposit as per the SBD? | The bidder is given additional time to submit the EMD | The Bid shall be summarily rejected | The EMD can be submitted after the bid opening | A penalty is imposed, and the bid is accepted | The bidder is disqualified from future tenders | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the THREE Packet system of e-tendering mentioned, in which packets are the documents for Packet A & B to be uploaded by the bidder? | Only in Packet A | Only in Packet B | In Packet A and Packet B online | In Packet C | Physical submission for Packet A and online for Packet B | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | Where can responsive and eligible bidders be present at the time of opening of bids? | At the Municipal Commissioner's office | Online only | In the office of the concerned Chief Engineer | At the site of work | At the Central Purchase Department | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When shall Packet C be opened in the three-packet system? | Automatically after opening Packet B | If bids submission in Packet A & B satisfies all requirements and are found acceptable | Simultaneously with Packet B | Before opening Packet A | Only after a physical verification of documents | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Who reserves the right to reject all or any of the e-tenders without assigning any reasons at any stage, as per the document? | The Chief Engineer of the concerned department | The State Government | The Municipal Commissioner | The bidders themselves | The Standing Committee | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the primary responsibility of the Municipal Corporation of Greater Mumbai (MCGM) in Greater Mumbai's urban governance, as stated in the Introduction? | To regulate traffic movement | To provide almost all kinds of engineering services and dedicated services in various segments | To manage the stock market | To conduct national elections | To operate the railway system | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What SAP module is used in the e-tendering process by MCGM, as mentioned in the document? | SAP FI | SAP MM | Supplier Relationship Module (SRM) | SAP HR | SAP PM | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the e-tendering process, what does the term "Supplier" or "Vendor" refer to? | The Municipal Corporation of Greater Mumbai | The Contractor/bidder | The Chief Engineer | The external auditor | The project manager | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | How can contractors already registered with MCGM (R3) get their User ID for E-tendering links? | By directly registering online as a new user | By approaching the Vendor Transfer cell and submitting their details | By contacting the Chief Engineer's office | By applying at the Central Purchase Department | By downloading the application form from the portal | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the minimum time in days that bidders should be given for submitting the bid for projects where a Pre-Bid meeting is provided? | 7 days | 15 days | 21 days | 10 days | 30 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Within how many days from the start of the sale of the tender should the Pre-Bid Meeting be scheduled? | Within the first 3 days | Between the 4th to 6th day | Between the 7th to 10th day | After the last date of sale of tender | On the day of bid opening | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | How is the value of executed works brought to the current costing level for assessing technical capacity in the eligibility criteria? | By adding a fixed percentage | By enhancing the actual value at a compound rate of 10% per annum from completion date to application receipt date | By taking the average value over the last 7 years | By adjusting based on the Consumer Price Index only | By considering only the original agreement value | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | For Regular, Routine, and Maintenance works, what does "Similar work" mean for assessing technical capacity? | Any civil construction work | Completed or ongoing works in specific categories like Building Construction/Maintenance, Road works, Sewerage/Water pipeline works, or culvert works | Works of any nature with similar estimated cost | Only works executed for MCGM | Works involving specialized technology | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the minimum average annual financial turnover required for Technical Capacity (Financial) in Regular, Routine and Maintenance works? | 20% of estimated cost | 30% of estimated cost | 40% of estimated cost | 50% of estimated cost | 10% of estimated cost | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | For Original and New construction works, what is one of the criteria for Technical Capacity (Project Experience) based on completed works? | Three similar completed works each costing 20% of estimated cost | Two similar completed works each costing 25% of estimated cost | One completed work of value equal to or not less than 40% of estimated cost | Three similar completed works each costing 30% of estimated cost | One completed work of value equal to or not less than 60% of estimated cost | 4 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Assessed Available Bid Capacity of prospective bidders calculated? | (A + N) * 2 - B | (A * N * 2) - B | (A + B) * N * 2 | A * N - B | (A - B) * N * 2 | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the Bid Capacity calculation formula, what does 'A' represent? | Average annual financial turnover | Maximum value of Civil Engineering works executed in any one year during the last five years | Estimated cost of the project | Value of existing commitments | Number of years for project completion | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | In the Bid Capacity calculation formula, what does 'N' represent? | Total number of projects completed | Number of years prescribed for completion of the Project/Works, excluding monsoon | Average number of monsoon periods in a year | Number of bidders participating in the tender | Number of technical staff required | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the Bid Capacity calculation formula, what does 'B' represent? | Total value of completed works | Value of existing commitments and on-going works to be completed during the project period | Bid Security Deposit amount | Cost of tender document | Overhead and profit percentage | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is a reason for which a bidder may be subject to disqualification even if they meet the qualifying criteria? | Submitting the bid online | Making misleading or false representation in the submitted documents | Attending the Pre-Bid meeting | Having a valid registration certificate | Submitting the bid before the deadline | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the validity period required for Bids after the deadline date for bid submission? | 90 days | 120 days | 180 days | 270 days | 365 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if a bid is valid for a shorter period than the minimum required validity period? | The bidder is asked to extend the validity period | The bid is accepted with a warning | The bid shall be rejected by the Employer as non-responsive | The bid is forwarded for technical evaluation | The EMD is partially forfeited | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When can the Employer request bidders to extend the period of validity of their bids? | Any time before the contract is awarded | In exceptional circumstances, prior to expiry of the original time limit | Only after the technical evaluation is completed | Only if there is a change in the scope of work | Only with the approval of the Municipal Commissioner | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the primary responsibility of the Contractor regarding the environment on and off the Site? | To plant trees on the site | To take all reasonable steps to protect the environment and avoid damage or nuisance from pollution, noise, etc. | To conduct environmental impact assessments | To comply only with central government environmental laws | To manage waste disposal within the site only | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the minimum percentage of the site that the Employer shall handover to the Contractor free of all encumbrances at the start of the work? | 50% | 60% | 75% | 90% | 100% | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | Within how many days in advance of the construction programme shall the Employer handover complete or part possession of the site to the Contractor? | 3 days | 5 days | 7 days | 10 days | 15 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if the Contractor fails to submit an updated Programme within the specified period? | The contract is terminated | A penalty is imposed per day of delay | The Engineer may withhold a specified amount from the next payment certificate | The Contractor is blacklisted | The project schedule is revised by the Engineer | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How often shall the Contractor submit to the Engineer for approval an updated Programme? | Weekly | Monthly | At intervals no longer than the period stated in the Contract Data | Quarterly | Annually | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the purpose of a Management Meeting that the Engineer may require the Contractor to attend? | To discuss payment issues | To review the plans for progress of the Works | To finalize the Bill of Quantities | To resolve legal disputes | To conduct a site inspection | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Who is responsible for the safety of all activities on the Site? | The Employer | The Engineer | The Contractor | The Municipal Commissioner | The safety consultant | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What should be done with anything of historical or other interest or of significant value unexpectedly discovered on the Site? | It becomes the property of the Contractor | It becomes the property of the Employer | It is to be sold by the Contractor | It should be reburied immediately | It is to be handed over to the local police | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the definition of a "Defect" in the context of the Contract? | A minor deviation from the plan | Any part of the Works not completed in accordance with the Contract | Damage caused by external factors | A delay in the completion of work | A change in the scope of work | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the purpose of the Defects Liability Certificate? | To certify the start of the work | To certify the completion of the work | Issued by the Engineer, after the Defect Liability Period has ended and upon correction of Defects | To certify the payment of the final bill | To certify the quality of materials used | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the required action by the Contractor if the Engineer asks to remove a person from the site, stating the reasons? | The Contractor must appeal the decision | The person must leave the Site within seven days and have no further connection with the Works | The Contractor can replace the person with someone else immediately | The Contractor must investigate the reasons provided by the Engineer | The decision is not binding on the Contractor | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the maximum percentage of the contract price that can be sub-let unless specifically mentioned in the contract? | 10% | 15% | 20% | 25% | 50% | 4 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | When is a Joint Venture (JV) generally allowed for a Project as per the SBD guidelines? | For any project, regardless of cost | Only when the number of identifiable different works is more than one and/or the estimated cost is more than Rs. 100 Crores | For routine maintenance works only | For projects with a completion period of less than 6 months | Only with foreign partners | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the minimum share of interest required for the lead member in a Joint Venture (JV) firm? | At least 20% | At least 30% | At least 51% | At least 40% | At least 10% more than the next highest member | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the technical eligibility of a JV firm typically judged for a work involving a single discipline? | The average technical capacity of all members is considered | The Lead member must meet at least 35% requirement of technical capacity | Any member can meet 100% of the requirement | The combined technical capacity of all members must be 100% | Based on the technical capacity of the member with the least experience | 2 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the requirement for the financial eligibility criteria of a JV firm? | The average annual turnover of all members must be 50% of the estimated cost | The contractual payments received by the JV or the arithmetic sum of payments by all members in any one of the last three financial years must be at least 100% of the estimated value | The net worth of the lead member must be 100% of the estimated cost | Any one member must have an annual turnover of 30% of the estimated cost | Based on the liquid assets of the JV firm only | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the maximum limit of Price Variation for a project with a time period of Above 24 months? | 5 Percent | 7.5 Percent | 10 Percent | 15 Percent | No limit | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | If the Contractor fails to complete the works by the contract or extended date, what is the compensation payable for delay for projects exceeding 6 months and not exceeding 2 years? | Maximum 1% per week | Maximum ½ percent per week | Maximum ¼ percent per week | A fixed amount per day | Based on the actual loss incurred by MCGM | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the maximum total amount of compensation for delay for a project with a completion period (originally stipulated or extended) exceeding 2 years? | 10 percent of the Contract Value | 7.5 percent of the Contract Value | 5 percent of the Contract Value | 15 percent of the Contract Value | No maximum limit | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the minimum required experience for a Project Manager with a degree for a work costing more than Rs. 100 Crore? | 5 years | 10 years | 12 years | 20 years | 15 years | 4 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the rate of recovery per month if a Project Manager with a degree and 20 years experience is not provided on a project? | Rs. 40,000/- | Rs. 50,000/- | Rs. 60,000/- | Rs. 30,000/- | Rs. 25,000/- | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Within how many days from the date of issue of the letter of acceptance shall all required documents for execution of the contract be submitted? | 7 days | 15 days | 30 days | 45 days | 60 days | 3 | 1 | 54 | 69 | MEDIUM | NA | NA
MSA | What is the penalty per day if the contract execution documents are not submitted within the stipulated time? | Rs. 1000/- | Rs. 2000/- | Rs. 5000/- | Rs. 10,000/- | 0.1% of the contract value | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the amount of Contract Deposit that the successful tenderer shall pay? | 1% of the contract sum | 2% of the contract sum | 5% of the contract sum | 10% of the contract sum | A fixed amount of Rs. 10,000/- | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When does the clause of retention money not applicable? | For works costing less than Rs. 1 Crore | For routine maintenance works | For M. & E. Department works | For works with a completion period of less than 6 months | For Joint Venture projects | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is Additional Security Deposit (ASD) applicable? | When a premium is quoted | When a rebate of more than 12% is quoted | For all works regardless of rebate/premium | Only for Original and New construction works | If the bidder has a record of poor performance | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Additional Security Deposit (ASD) calculated when applicable? | Percentage rebate quoted x Estimated cost | (Percentage rebate quoted above 12% / 100) x office estimated cost | Percentage rebate quoted above 12% x Contract sum | 10% of the Contract Sum | 5% of the Estimated Cost | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Performance Guarantee (PG) applicable for premium, at par, and rebate 0 to 12%? | 1% of contract sum | 2% of contract sum | 0.92% x contract sum applicable for rebate of 12% | 5% of contract sum | 10% of contract sum | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When shall the Bid Security/EMD of L-3 and other bidders (excluding L-1 and L-2) be refunded? | After signing of the Agreement | Immediately after opening of financial bid | After completion of the Defects Liability Period | After obtaining Standing Committee Resolution | After the work is completed | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When will the EMD/ASD submitted by the L-2 bidder be returned? | Immediately after opening of financial bid | After obtaining Standing Committee Resolution | After signing of the Agreement | After completion of the Defects Liability Period | After the work is completed | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered an "Intentional Avoidance" by a contractor, which can lead to disciplinary action? | Attending the Pre-Bid meeting | Non-submission of required documents in Packet "A" after communication of shortfalls | Quoting a high rebate | Having a valid registration certificate | Submitting the bid online before the deadline | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What are considered "Curable Defects" in the submission of tender documents? | In-adequate submission of EMD/ASD amount | Shortfalls in submission of documents like Registration Certificate, Bank Solvency, PAN, etc. | In-adequacy of technical and financial capacity | Quoting a very low percentage | Not attending the Pre-Bid meeting | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered a "Non-curable Defect" in the submission of tender documents? | Non-submission of a valid Registration Certificate | In-adequate submission of EMD/ASD amount | Non-submission of certified copies of PAN documents | Wrong calculation of Bid Capacity | No proper submission of experience certificates | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the validity period required for the Performance Guarantee (PG)? | Until the work is completed | Until the Defect Liability Period or finalization of final bill whichever is later | For a period of 1 year from the date of issue | Until the Commencement Certificate is issued | Until the Occupancy Certificate is issued | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Refund of Contract Deposit processed for works having a 5-year DLP? | Within 30 days of issue of Completion Certificate | Within 30 days after completion of 3rd year of DLP and after issue of 'Defect Liability Certificate' | After finalization of the final bill | Immediately after completion of the work | After the end of the 5-year DLP | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is one-half (50%) of the Retention Money released? | Within 30 days of issue of Commencement Certificate | Within 30 days of issue of 'Certificate of Completion' with respect to the whole of the Works | After completion of the Defects Liability Period | Along with the final bill payment | After obtaining the Occupancy Certificate | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the validity period required for a Bank Guarantee obtained in lieu of a deposit? | Until the work is completed | Further 6 months from the completion of defect liability period/ warranty period | Until the Letter of Acceptance is issued | Until the Commencement Certificate is issued | Until the final bill is paid | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if the bidder fails to keep the submitted Bank Guarantee "VALID" for the stipulated time period? | The bidder is given a grace period to renew it | It will attract penalization | The work is stopped temporarily | The Contract Deposit is forfeited | The bidder is disqualified from the current tender only | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the maximum Legal + Stationery Charges for a contract value from Rs. 1,00,00,001/- to Any amount? | Rs. 2420/- | Rs. 6050/- | Rs. 30,000/- | Rs. 1,00,000/- | Nil | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the basis for the tender being prepared according to the Specifications & Selection of Material section? | National Building Code | Indian Standards (IS) Codes | Unified Schedule of Rates and specifications 2013 | Contractor's own specifications | Previous project specifications | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How can a deserving contractor obtain the specifications of the items of the Unified Schedule of Rates (USOR)? | By purchasing a separate document | By downloading from the MCGM portal under the Tender tab or collecting a soft copy when purchasing the tender | Only through a physical copy from the Chief Engineer's office | They are provided as part of the Bill of Quantities | They are not publicly available | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Who is responsible for ensuring that the materials brought on the site are the best of their respective kinds and to the approval of the Engineer? | The Engineer's Representative | The Engineer | The Contractor | The supplier of the materials | The Quality Control Engineer | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if any materials brought on the works have not been found to conform to the specifications? | They can be used with a reduced payment | They will be rejected forthwith and shall be removed from the site by the contractor at his own cost within 24 hours | The Engineer will decide on a case-by-case basis | They can be stored on site for future use | The contractor is given a warning | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "corrupt practice" mean according to the Fraud and Corrupt Practices section? | Any delay in the bidding process | The offering, giving, receiving, or soliciting anything of value to influence actions in the Bidding Process | Failure to submit required documents | Not attending the Pre-Bid meeting | Quoting a very high price | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "fraudulent practice" mean according to the Fraud and Corrupt Practices section? | Forming a cartel with other bidders | A misrepresentation or omission of facts or suppression of facts to influence the Bidding Process | Impairing or harming any person or property to influence participation | Establishing contact with MCGM officials to lobby | Not disclosing payments made to intermediaries before signing the contract | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "coercive practice" mean according to the Fraud and Corrupt Practices section? | Delaying the submission of bids | Impairing or harming or threatening to impair or harm any person or property to influence participation or action in the Bidding Process | Misrepresenting facts in the bid document | Forming a cartel to manipulate competition | Not providing required information | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "restrictive practice" mean according to the Fraud and Corrupt Practices section? | Delaying the completion of work | Forming a cartel or arriving at any understanding among Applicants to restrict or manipulate competition | Making false statements to investigators | Not allowing access to the site for inspection | Not providing necessary safety equipment | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Where shall the arbitration proceedings be held in case of disputes? | At the Municipal Commissioner's office | At a location outside Mumbai limits | At such place and time within the limits of Brihan Mumbai as the arbitrator may determine | At the High Court | At the site of work | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Within how many days from the receipt of notice of decision from the Municipal Commissioner can a Contractor refer a dispute to arbitration? | 30 days | 60 days | 90 days | 180 days | 7 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the time period within which the Engineer In-charge shall check the Contractor's fortnightly/monthly payment statement? | 7 days | 10 days | 14 days | 21 days | 30 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Within how many days shall the Employer pay the Contractor the amounts certified by the Engineer? | 10 days | 14 days | 15 days | 30 days | 45 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | According to the SBD, when shall no payment be made for any work estimated to cost less than Rupees One Thousand? | Until 50% of the work is completed | Until a monthly bill is submitted | Till after the whole of work shall have been completed and the certificate of completion given | Only at the discretion of the Engineer | If the work is delayed | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the stipulated percentage of the value of work done that can be paid as an adhoc payment to the contractor on request? | Upto 50% | Upto 60% | Upto 75% | Upto 90% | Upto 100% | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is price variation not made applicable for contracts according to the Price Variation Clause? | For contracts upto 6 months | For contracts upto 12 months | For contracts upto 18 months | For contracts upto 24 months | For contracts of any duration | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the formula given for calculating the Price Variation for the Labour component? | VL = (0.88 R) x 30 x ( I – IO) / 100 WO | VL = (0.88 R) x 70 x ( I – IO) / 100 IO | VL = (0.88 R) x 30 x ( I – IO) / 100 IO | VL = (R) x 30 x ( I – IO) / 100 IO | VL = (0.88 R) x ( I – IO) / 100 IO | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the formula for Material component price variation (VM), what does 'WO' represent? | Average wholesale price index for the period under reference | Wholesale price index prevailing on the day of 28 days prior to the date of submission of the tender | Wholesale price index at the start date of the work | Wholesale price index at the completion date of the work | Average wholesale price index over the contract period | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | For projects with a time period of Above 12 months to 24 months, what is the Maximum limit of Price Variation? | No variation allowed | 5% | 10% | 15% | 20% | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | If an extension of time is granted for reasons not attributable to MCGM and Contractor, how is the price variation for the extended period limited? | Limited to the amount payable as per the Indices applicable to the last month of the original period | Limited to the amount payable as per the Indices at the start date of the extended period | Limited to 5% of the contract value for the extended period | No price variation is allowed for the extended period | Based on mutual agreement between the Contractor and Engineer | 1 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the process for settlement of disputes if a dispute arises between the Employer and the Contractor or Engineer and Contractor? | Directly refer to arbitration | Refer to the Municipal Commissioner within 7 days | Refer to the concerned Addl. Municipal Commissioner who shall constitute a committee | File a case in the High Court | Refer to the Chief Engineer for a final decision | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Within how many days shall the committee constituted by the Addl. Municipal Commissioner give a written decision on a dispute? | 7 days | 30 days | 60 days | 90 days | 180 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | To whom can an appeal on the Order of the committee constituted by the Addl. Municipal Commissioner be referred? | The Chief Engineer | The Standing Committee | The Municipal Commissioner | The State Government | The Arbitrator | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | If the Municipal Commissioner has given written notice of the decision and no Claim to arbitration has been communicated within a period of 90 days, what is the consequence? | The Contractor can still refer to arbitration later | The decision shall remain final and binding upon the Contractor | The decision is open for negotiation | The Contractor can file a case in court | The Security Deposit is forfeited | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Who shall effect arbitration if agreed upon by the parties? | The Municipal Commissioner | A committee of three engineers | A single arbitrator | The Chief Engineer | The Standing Committee | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the jurisdiction for all legal proceedings in respect of any claim, dispute, or difference arising in respect of a contract? | The place where the work is executed | Any competent court in Maharashtra | A competent court in the City of Mumbai only | The High Court of Mumbai | The Supreme Court of India | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What shall remain vested in the Contractor or his sub-contractors regarding drawings and other documents provided under the contract? | The physical copies of the documents | The copyright of all drawings and other documents | The ownership of the intellectual property rights | The right to use the documents for other projects | The responsibility for the accuracy of the drawings | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What information submitted by the Authority or submitted by an Applicant to the Authority shall remain or become the property of the Authority? | Only the financial information | All documents and other information | Only the technical drawings | Only the bid security deposit | Only the signed agreement | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | If a Contractor fails to submit their bills within 45 days from the date of completion/running bill, what is the consequence for the bill? | A penalty of 5% of the bill amount is imposed | A penalty of 10% of the bill amount is imposed | The Bill will not be admitted for payment | The payment is delayed by 90 days | The bill is processed with a deduction of 20% | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the action to be taken if the penalisation amount for bad work and not done as per specifications exceeds the maximum limit with respect to Clause 8.e? | The contract is immediately terminated | A show cause notice shall necessarily be issued to the contractor as to why the contract should not be terminated | The contractor is given a warning and time to rectify the work | The Security Deposit is forfeited without notice | The matter is referred to arbitration | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When shall the Engineer-in-charge issue notice to the contractor for rectifying defects or redoing of the work? | After the Defects Liability Period has ended | If any work has been executed with unsound, imperfect or unskillful workmanship or with inferior materials | Only if the defects affect the safety of the structure | Upon completion of the work | At the request of the Municipal Commissioner | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the primary mode of submission for e-tenders for MCGM works as per the SBD? | Physical submission only | Online submission through the designated portal | Submission via email | Submission via post | Submission through a third-party agency | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the three-stage system of e-tendering, what are the main packets to be submitted by the bidder? | Packet A and Packet B only | Packet A, Packet B, and Packet C | Packet A, Packet B, Packet C, and Packet D | Only Packet A and Packet C | Only Packet B and Packet C | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does Packet A typically contain in the three-packet e-tendering system? | Financial Bid | Commercial Bid and Technical Bid | Statutory documents and Bid Security | Bill of Quantities | Drawings and Specifications | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does Packet B typically contain in the three-packet e-tendering system? | Financial Bid | Technical Bid and other relevant documents to assess technical capacity | Statutory documents and Bid Security | Bill of Quantities | Drawings and Specifications | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does Packet C typically contain in the three-packet e-tendering system? | Statutory documents and Bid Security | Technical Bid and other relevant documents | Financial Bid (Bill of Quantities with quoted rates) | Drawings and Specifications | Eligibility Criteria | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Bid Security (EMD) primarily required to be submitted by the bidders in the e-tendering process? | Via Demand Draft | Through the online payment gateway provided on the e-tendering portal | Via Bank Guarantee in Packet A | Directly at the MCGM cash counter | Via a physical challan | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if a bid is submitted without the required Earnest Money Deposit (EMD)? | The bidder is given additional time to submit the EMD. | The Bid shall be summarily rejected. | The EMD can be submitted after the opening of Packet A. | A penalty is imposed, and the bid is accepted. | The bidder is disqualified from the current tender process. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the purpose of a Pre-Bid Meeting as described in the SBD? | To open the financial bids. | To clarify any doubts regarding the tender document and scope of work, and to address queries from prospective bidders. | To assess the financial capacity of the bidders. | To sign the contract agreement. | To physically inspect the site. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Where are the bid submission requirements and deadlines specified in the SBD? | In the Scope of Work section. | In the E-Tender Notice and Instructions to Applicants sections. | In the General Conditions of Contract. | In the Bill of Quantities. | In the Appendix. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Who has the right to reject any or all bids received without assigning any reason? | The Chief Engineer of the concerned department. | The Municipal Commissioner. | The Standing Committee. | The bidders themselves. | The Government of Maharashtra. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the required validity period for the bids submitted by the bidders? | 90 days from the date of bid submission. | 120 days from the date of bid submission. | 180 days from the deadline date for bid submission. | Until the work is completed. | Until the Defects Liability Period is over. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What happens if a bidder provides a bid validity period shorter than the minimum required in the SBD? | The bid is accepted with a warning. | The bid shall be rejected by the Employer as non-responsive. | The bidder is asked to extend the validity period. | A penalty is imposed on the bidder. | The EMD is partially forfeited. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Under what circumstances may the Employer request the bidders to extend the period of validity of their bids? | Any time after the bids are opened. | In exceptional circumstances, prior to the expiry of the original bid validity period. | Only after the financial bids have been opened. | If there is a change in the scope of work. | Only with the approval of the Standing Committee. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the main purpose of establishing Eligibility Criteria for bidders in the SBD? | To limit the number of bidders. | To ensure that the bidders have the necessary technical and financial capacity to execute the work. | To generate revenue from the tender process. | To provide a level playing field for all bidders. | To discourage small contractors from bidding. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the technical capacity of a bidder generally assessed for similar works? | Based on the total value of all works executed by the bidder. | Based on the experience of having successfully completed similar works of a certain magnitude within a specified period. | Based on the number of engineers employed by the bidder. | Based on the machinery owned by the bidder. | Based on the bidder's financial turnover in the last year. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the minimum average annual financial turnover required for technical capacity in Regular, Routine, and Maintenance works, as per the SBD? | 20% of the estimated cost. | 30% of the estimated cost of work in the last three financial years. | 40% of the estimated cost. | 50% of the estimated cost. | 10% of the estimated cost. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Assessed Available Bid Capacity of prospective bidders calculated as per the SBD? | (A + N) * 2 - B | (A * N * 2) - B | (A + B) * N * 2 | A * N - B | (A - B) * N * 2 | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the formula for Assessed Available Bid Capacity, what does 'A' represent? | Average annual financial turnover. | Maximum value of Civil Engineering works executed in any one year during the last five years (updated to current price level).1 | Estimated cost of the project. | Value of existing commitments and ongoing works. | Number of years for project completion. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the formula for Assessed Available Bid Capacity, what does 'N' represent? | Total number of projects completed. | Number of years prescribed for completion of the Project/Works, excluding monsoon period (with 0.33 added for every intervening monsoon). | Average number of monsoon periods in a year. | Number of bidders participating. | Number of technical staff required. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the formula for Assessed Available Bid Capacity, what does 'B' represent? | Total value of completed works. | Value of existing commitments and ongoing works to be completed during the project period. | Bid Security Deposit amount. | Cost of tender document. | Overhead and profit percentage. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is a potential reason for disqualification of a bidder, even if they meet the eligibility criteria, as per the SBD? | Submitting the bid online before the deadline. | Making misleading or false representation in the submitted documents or having a record of poor performance. | Attending the Pre-Bid meeting. | Having a valid registration certificate. | Submitting the bid in the prescribed format. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the primary purpose of the "Declaration by the Bidder" form included in the SBD? | To provide a list of subcontractors. | To declare that the information provided in the bid is true and correct, and to undertake to abide by the tender conditions. | To propose alternative designs for the work. | To request for an advance payment. | To declare the ownership of machinery. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if a bidder is found to have made a misleading or false representation in the documents submitted? | The bidder is given a warning. | The bidder may be disqualified and face disciplinary action, including blacklisting. | The bidder is asked to correct the information. | A penalty is imposed on the bidder. | The bid is accepted, but with reduced weightage for technical capacity. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the validity period required for the Bank Guarantee submitted towards Bid Security/EMD? | Until the bid opening date. | Until the bid validity period plus an extra period as specified in the SBD. | Until the work is completed. | Until the Defects Liability Period is over. | Until the final bill is paid. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is the Bid Security/EMD of the unsuccessful bidders (excluding L-1 and L-2) typically refunded? | Immediately after the opening of Packet C (Financial Bid). | Immediately after the opening of Packet A and Packet B if the bidder is found non-responsive. | After the contract agreement is signed with L-1. | After the completion of the work. | After the Defects Liability Period is over. | 1 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is the Bid Security/EMD submitted by the L-2 bidder typically returned? | Immediately after the opening of Packet C. | After the Standing Committee Resolution regarding the tender is obtained. | After the contract agreement is signed with L-1. | After the completion of the work. | After the Defects Liability Period is over. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the required action by the successful bidder (L-1) after receiving the Letter of Acceptance? | To start the work immediately. | To submit the required Contract Deposit, execute the formal agreement, and fulfill other pre-contractual formalities within the stipulated time. | To submit the final bill for payment. | To apply for the Occupancy Certificate. | To attend a meeting with the Municipal Commissioner. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the timeframe within which the successful bidder must submit the necessary documents for contract execution and sign the agreement after the Letter of Acceptance is issued? | 7 days | 15 days | 30 days | 45 days | 60 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the penalty per day if the successful bidder fails to submit the contract execution documents and sign the agreement within the stipulated timeframe? | Rs. 1000/- per day | Rs. 2000/- per day | Rs. 5000/- per day | Rs. 10,000/- per day | 0.1% of the contract value per day | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the amount of Contract Deposit that the successful bidder is required to pay? | 1% of the contract sum. | 2% of the contract sum. | 5% of the contract sum. | 10% of the contract sum. | A fixed amount as specified in the tender notice. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Retention Money that is typically recovered from the Contractor's running bills? | 2% | 3% | 5% | 7.5% | 10% | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Under what circumstances is Additional Security Deposit (ASD) applicable in the tender process? | When a premium is quoted by the bidder. | When a rebate of more than 12% is quoted by the bidder. | For all tenders regardless of the quoted rate. | Only for Original and New Construction works. | If the bidder has a history of delayed projects. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Additional Security Deposit (ASD) calculated when applicable? | Percentage rebate quoted x Estimated cost. | (Percentage rebate quoted above 12% / 100) x office estimated cost. | Percentage rebate quoted above 12% x Contract sum. | 10% of the Contract Sum. | 5% of the Estimated Cost. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Performance Guarantee (PG) required for tenders with premium, at par, and rebate up to 12%? | 1% of the contract sum. | 2% of the contract sum. | 0.92% x contract sum applicable for rebate of 12%. | 5% of the contract sum. | 10% of the contract sum. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the required validity period for the Performance Guarantee (PG)? | Until the work is completed. | Until the Defects Liability Period or finalization of the final bill, whichever is later. | For a period of 1 year from the date of issue. | Until the Commencement Certificate is issued. | Until the Occupancy Certificate is issued. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the consequence if the contractor fails to keep the submitted Bank Guarantee "VALID" for the stipulated time period? | The contractor is given a grace period to renew it. | It will attract penalization as per the contract conditions. | The work is stopped temporarily. | The Contract Deposit is forfeited. | The contractor is disqualified from future tenders. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the role of the Engineer-in-charge in the administration of the contract? | To execute the work. | To supervise the work, interpret the contract documents, approve materials and workmanship, certify payments, and manage the contract. | To provide labor for the work. | To arrange for the necessary machinery. | To collect payments from the Employer. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the contractor's responsibility regarding the quality of materials and workmanship? | To use materials provided by the Employer only. | To use materials and execute workmanship of the best respective kinds in accordance with the contract and to the satisfaction of the Engineer. | To use the cheapest available materials. | To follow their own standards for quality. | To obtain approval for materials after they are incorporated in the work. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What happens if any materials brought on the works are not found to conform to the specifications? | They can be used with a reduced payment. | They will be rejected forthwith and shall be removed from the site by the contractor at his own cost within 24 hours. | The Engineer2 will decide on a case-by-case basis. | They can be stored on site for future use. | The contractor is given a warning. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "corrupt practice" mean according to the Fraud and Corrupt Practices clause in the SBD? | Any delay in the bidding process. | The offering, giving, receiving, or soliciting directly or indirectly of anything of value to influence the actions of any person in the Bidding Process. | Failure to submit required documents. | Not attending the Pre-Bid meeting. | Quoting a very low price. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "fraudulent practice" mean according to the Fraud and Corrupt Practices clause in the SBD? | Forming a cartel with other bidders. | A misrepresentation or omission of facts or suppression of facts in order to influence the Bidding Process. | Impairing or harming any person or property to influence participation. | Establishing contact with MCGM officials to lobby. | Not disclosing payments made to intermediaries before signing the contract. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "coercive practice" mean according to the Fraud and Corrupt Practices clause in the SBD? | Delaying the submission of bids. | Impairing or harming or threatening to impair or harm, directly or indirectly, any person or the property of the person to influence3 decisions or participation in the Bidding Process. | Misrepresenting facts in the bid document. | Forming a cartel to manipulate competition. | Not providing required information. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What does "restrictive practice" mean according to the Fraud and Corrupt Practices clause in the SBD? | Delaying the completion of work. | Forming a cartel or arriving at any understanding or arrangement among bidders with the objective of restricting or manipulating competition. | Making false statements to investigators. | Not allowing access to the site for inspection. | Not providing necessary safety equipment. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Where shall the arbitration proceedings be held in case of disputes arising from the contract? | At the Municipal Commissioner's office. | At such place and time within the limits of Brihan Mumbai as the arbitrator may determine. | At a location outside Mumbai limits. | At the High Court. | At the site of work. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | Within how many days from the receipt of notice of decision from the Municipal Commissioner can a Contractor refer a dispute to arbitration? | 30 days | 60 days | 90 days | 180 days | 7 days | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the stipulated percentage of the value of work done that can be paid as an adhoc payment to the contractor on request? | Upto 50% | Upto 60% | Upto 75% | Upto 90% | Upto 100% | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is price variation not applicable for contracts according to the Price Variation Clause? | For contracts upto 6 months. | For contracts upto 12 months. | For contracts upto 18 months. | For contracts upto 24 months. | For contracts of any duration. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the formula given for calculating the Price Variation for the Labour component (VL)? | VL = (0.88 R) x 30 x ( I – IO) / 100 WO | VL = (0.88 R) x 70 x ( I – IO) / 100 IO | VL = (0.88 R) x 30 x ( I – IO) / 100 IO | VL = (R) x 30 x ( I – IO) / 100 IO | VL = (0.88 R) x ( I – IO) / 100 IO | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | In the formula for Material component price variation (VM), what does 'WO' represent? | Average wholesale price index for the period under reference. | Wholesale price index prevailing on the day of 28 days prior to the deadline for submission of tenders. | Wholesale price index at the start date of the work. | Wholesale price index at the completion date of the work. | Average wholesale price index over the contract period. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | For projects with a time period of Above 12 months to 24 months, what is the Maximum limit of Price Variation? | No variation allowed. | 5% | 10% | 15% | 20% | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | If an extension of time is granted for reasons not attributable to MCGM and Contractor, how is the price variation for the extended period limited? | Limited to the amount payable as per the Indices applicable to the last month of the original period. | Limited to the amount payable as per the Indices at the start date of the extended period. | Limited to 5% of the contract value for the extended period. | No price variation is allowed for the extended period. | Based on mutual agreement between the Contractor and Engineer. | 1 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the maximum total amount of compensation for delay for a project with a completion period (originally stipulated or extended) exceeding 2 years? | 10 percent of the Contract Value. | 7.5 percent of the Contract Value. | 5 percent of the Contract Value. | 15 percent of the Contract Value. | No maximum limit. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the minimum required experience for a Project Manager with a degree for a work costing more than Rs. 100 Crore? | 5 years | 10 years | 12 years | 20 years | 15 years | 4 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the rate of recovery per month if a Project Manager with a degree and 20 years experience is not provided on a project? | Rs. 40,000/- p.m. | Rs. 50,000/- p.m. | Rs. 60,000/- p.m. | Rs. 30,000/- p.m. | Rs. 25,000/- p.m. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the penalty per day if the contract execution documents are not submitted within the stipulated time? | Rs. 1000/- per day | Rs. 2000/- per day | Rs. 5000/- per day | Rs. 10,000/- per day | 0.1% of the contract value per day | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the amount of Contract Deposit that the successful tenderer shall pay? | 1% of the contract sum. | 2% of the contract sum. | 5% of the contract sum. | 10% of the contract sum. | A fixed amount of Rs. 10,000/-. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Retention Money that will be recovered from the contractor's every bill? | 2 percent | 3 percent. | 5 percent. | 7.5 percent. | 10 percent. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When does the clause of retention money not applicable? | For works costing less than Rs. 1 Crore. | For routine maintenance works. | For M. & E. Department works. | For works with a completion period of less than 6 months. | For Joint Venture projects. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is Additional Security Deposit (ASD) applicable? | When a premium is quoted. | When a rebate of more than 12% is quoted. | For all works regardless of rebate/premium. | Only for Original and New construction works. | If the bidder has a record of poor performance. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Additional Security Deposit (ASD) calculated when applicable? | Percentage rebate quoted x Estimated cost. | (Percentage rebate quoted above 12% / 100) x office estimated cost. | Percentage rebate quoted above 12% x Contract sum. | 10% of the Contract Sum. | 5% of the Estimated Cost. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Performance Guarantee (PG) applicable for premium, at par, and rebate 0 to 12%? | 1% of contract sum. | 2% of contract sum. | 0.92% x contract sum applicable for rebate of 12%. | 5% of contract sum. | 10% of contract sum. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When shall the Bid Security/EMD of L-3 and other bidders (excluding L-1 and L-2) be refunded? | After signing of the Agreement. | Immediately after opening of financial bid. | After completion of the Defects Liability Period. | After obtaining Standing Committee Resolution. | After the work is completed. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When will the EMD/ASD submitted by the L-2 bidder be returned? | Immediately after opening of financial bid. | After obtaining Standing Committee Resolution. | After signing of the Agreement. | After completion of the Defects Liability Period. | After the work is completed. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered an "Intentional Avoidance" by a contractor, which can lead to disciplinary action? | Attending the Pre-Bid meeting. | Non-submission of required documents in Packet "A" after communication of shortfalls, if three or more cases occur in 12 months. | Quoting a high rebate. | Having a valid registration certificate. | Submitting the bid online before the deadline. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What are considered "Curable Defects" in the submission of tender documents? | In-adequate submission of EMD/ASD amount. | Shortfalls in submission of documents like Valid Registration Certificate, Valid Bank Solvency, Sales Tax Registration Certificate, Certified Copies of PAN, Partnership Deed, Undertakings, wrong calculation of Bid Capacity, no proper submission of experience certificates. | In-adequacy of technical and financial capacity. | Quoting a very low percentage. | Not attending the Pre-Bid meeting. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered a "Non-curable Defect" in the submission of tender documents? | Non-submission of a valid Registration Certificate. | In-adequate submission of EMD/ASD amount or in-adequacy of technical and financial capacity with respect to Eligibility criteria. | Non-submission of certified copies of PAN documents. | Wrong calculation of Bid Capacity. | No proper submission of experience certificates. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the validity period required for the Performance Guarantee (PG)? | Until the work is completed. | Until the defect liability period or finalization of final bill whichever is later. | For a period of 1 year from the date of issue. | Until the Commencement Certificate is issued. | Until the Occupancy Certificate is issued. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the amount of Contract Deposit that the successful tenderer shall pay? | 1% of the contract sum. | 2% of the contract sum. | 5% of the contract sum. | 10% of the contract sum. | A fixed amount of Rs. 10,000/-. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Retention Money that will be recovered from the contractor's every bill? | 2 percent | 3 Percent. | 5 Percent. | 7.5 Percent. | 10 Percent. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When does the clause of retention money not applicable? | For works costing less than Rs. 1 Crore. | For routine maintenance works. | For M. & E. Department works. | For works with a completion period of less than 6 months. | For Joint Venture projects. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is Additional Security Deposit (ASD) applicable? | When a premium is quoted. | When a rebate of more than 12% is quoted. | For all works regardless of rebate/premium. | Only for Original and New construction works. | If the bidder has a record of poor performance. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Additional Security Deposit (ASD) calculated when applicable? | Percentage rebate quoted x Estimated cost. | (Percentage rebate quoted above 12% / 100) x office estimated cost. | Percentage rebate quoted above 12% x Contract sum. | 10% of the Contract Sum. | 5% of the Estimated Cost. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Performance Guarantee (PG) applicable for premium, at par, and rebate 0 to 12%? | 1% of contract sum. | 2% of contract sum. | 0.92% x contract sum applicable for rebate of 12%. | 5% of contract sum. | 10% of contract sum. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When shall the Bid Security/EMD of L-3 and other bidders (excluding L-1 and L-2) be refunded? | After signing of the Agreement. | Immediately after opening of financial bid. | After completion of the Defects Liability Period. | After obtaining Standing Committee Resolution. | After the work is completed. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When will the EMD/ASD submitted by the L-2 bidder be returned? | Immediately after opening of financial bid. | After obtaining Standing Committee Resolution. | After signing of the Agreement. | After completion of the Defects Liability Period. | After the work is completed. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered an "Intentional Avoidance" by a contractor, which can lead to disciplinary action? | Attending the Pre-Bid meeting. | Non-submission of required documents in Packet "A" after communication of shortfalls, if three or more cases occur in 12 months. | Quoting a high rebate. | Having a valid registration certificate. | Submitting the bid online before the deadline. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What are considered "Curable Defects" in the submission of tender documents? | In-adequate submission of EMD/ASD amount. | Shortfalls in submission of documents like Valid Registration Certificate, Valid Bank Solvency, Sales Tax Registration Certificate, Certified Copies of PAN, Partnership Deed, Undertakings, wrong calculation of Bid Capacity, no proper submission of experience certificates. | In-adequacy of technical and financial capacity. | Quoting a very low percentage. | Not attending the Pre-Bid meeting. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered a "Non-curable Defect" in the submission of tender documents? | Non-submission of a valid Registration Certificate. | In-adequate submission of EMD/ASD amount or in-adequacy of technical and financial capacity with respect to Eligibility criteria. | Non-submission of certified copies of PAN documents. | Wrong calculation of Bid Capacity. | No proper submission of experience certificates. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the validity period required for the Performance Guarantee (PG)? | Until the work is completed. | Until the defect liability period or finalization of final bill whichever is later. | For a period of 1 year from the date of issue. | Until the Commencement Certificate is issued. | Until the Occupancy Certificate is issued. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the amount of Contract Deposit that the successful tenderer shall pay? | 1% of the contract sum. | 2% of the contract sum. | 5% of the contract sum. | 10% of the contract sum. | A fixed amount of Rs. 10,000/-. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Retention Money that will be recovered from the contractor's every bill? | 2%. | 3%. | 5%. | 7.5%. | 10%. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When does the clause of retention money not applicable? | For works costing less than Rs. 1 Crore. | For routine maintenance works. | For M. & E. Department works. | For works with a completion period of less than 6 months. | For Joint Venture projects. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When is Additional Security Deposit (ASD) applicable? | When a premium is quoted. | When a rebate of more than 12% is quoted. | For all works regardless of rebate/premium. | Only for Original and New construction works. | If the bidder has a record of poor performance. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | How is the Additional Security Deposit (ASD) calculated when applicable? | Percentage rebate quoted x Estimated cost. | (Percentage rebate quoted above 12% / 100) x office estimated cost. | Percentage rebate quoted above 12% x Contract sum. | 10% of the Contract Sum. | 5% of the Estimated Cost. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the percentage of Performance Guarantee (PG) applicable for premium, at par, and rebate 0 to 12%? | 1 % of contract sum. | 2 % of contract sum. | 0.92 % x contract sum applicable for rebate of 12%. | 5 % of contract sum. | 10 % of contract sum. | 3 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When shall the Bid Security/EMD of L-3 and other bidders (excluding L-1 and L-2) be refunded? | After signing of the Agreement. | Immediately after opening of financial bid. | After completion of the Defects Liability Period. | After obtaining Standing Committee Resolution. | After the work is completed. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | When will the EMD/ASD submitted by the L-2 bidder be returned? | Immediately after opening of financial bid. | After obtaining Standing Committee Resolution. | After signing of the Agreement. | After completion of the Defects Liability Period. | After the work is completed. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered an "Intentional Avoidance" by a contractor, which can lead to disciplinary action? | Attending the Pre-Bid meeting. | Non-submission of required documents in Packet "A" after communication of shortfalls, if three or more cases occur in 12 months. | Quoting a high rebate. | Having a valid registration certificate. | Submitting the bid online before the deadline. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What are considered "Curable Defects" in the submission of tender documents? | In-adequate submission of EMD/ASD amount. | Shortfalls in submission of documents like Valid Registration Certificate, Valid Bank Solvency, Sales Tax Registration Certificate, Certified Copies of PAN, Partnership Deed, Undertakings, wrong calculation of Bid Capacity, no proper submission of experience certificates. | In-adequacy of technical and financial capacity. | Quoting a very low percentage. | Not attending the Pre-Bid meeting. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is considered a "Non-curable Defect" in the submission of tender documents? | Non-submission of a valid Registration Certificate. | In-adequate submission of EMD/ASD amount or in-adequacy of technical and financial capacity with respect to Eligibility criteria. | Non-submission of certified copies of PAN documents. | Wrong calculation of Bid Capacity. | No proper submission of experience certificates. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the validity period required for the Performance Guarantee (PG)? | Until the work is completed. | Until the defect liability period or finalization of final bill whichever is later. | For a period of 1 year from the date of issue. | Until the Commencement Certificate is issued. | Until the Occupancy Certificate is issued. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA
MSA | What is the amount of Contract Deposit that the successful tenderer shall pay? | 1% of the contract sum. | 2% of the contract sum. | 5% of the contract sum. | 10% of the contract sum. | A fixed amount of Rs. 10,000/-. | 2 | 1 | 54 | 69 | VERYEASY | NA | NA